THE SILENT BURDEN

Understanding Male Suicide in the United Kingdom

Portfolio Project — Full Master Plan

Kudzanayi Shepherd Mhlanga  |  Senior Vehicle Engineer, Go Ahead London  |  Sutton, London  |  June 2026

Every two hours, a man in the United Kingdom dies by suicide. Most of them never asked for help.

# Project Overview

This project combines three disciplines into a single, portfolio-defining body of work: a research project investigating the causes and patterns of male suicide in the UK, a data analytics project with predictive modelling using ONS and NHS data, and a documentary storytelling project bringing the human reality behind the numbers to life.

Core Question:

Why are men in the United Kingdom significantly more likely to die by suicide, yet significantly less likely to seek help?

## Target Audience

| Audience | Why They Matter |
| --- | --- |
| Men aged 18–65 | Primary subject — the ones carrying the burden |
| Families and partners | Often the first to notice signs |
| Employers and managers | Workplace is where crisis first becomes visible |
| Policymakers | Data-driven findings can inform NHS funding decisions |
| Mental health organisations | Samaritans, Mind, CALM — potential collaborators |

# Key Statistics (United Kingdom)

| Metric | Statistic | Source |
| --- | --- | --- |
| Male suicide rate — England & Wales (2024) | 17.6 per 100,000 | ONS |
| Male share of all UK suicides | ~75% | ONS / Samaritans |
| Highest risk age group (males) | 50–54 years (27.5/100,000) | ONS 2024 |
| Suicide — leading cause of death | Men under 50 | ONS |
| Highest regional rate | North East England (15.1/100,000) | ONS |
| Wales male rate (2024) | 25.0 per 100,000 | ONS / CPRMB |
| Men accessing psychological therapy | Less than half the female rate | NHS |

# Documentary Story Structure

## Act 1 — The Silence

Opening with ordinary British life: a mechanic working alone, a bus driver finishing a night shift, a father at a quiet dinner table, a young professional staring at a laptop. Voice-over introduces the reality that men carry invisible burdens and rarely speak about them.

## Act 2 — The Numbers

Data presented visually — male suicide trends 2000–2024, age breakdowns, regional disparities, deprivation correlation, and the gap in mental health service access. Poses the question: what happens when men feel they have nowhere to turn?

## Act 3 — Real Voices

Interviews and scripted character profiles covering: Marcus (mechanic, divorced father), Derek (bus driver, redundancy), Callum (young professional, isolation), Jamie (veteran, Scotland), and Linda (bereaved mother, Wales). Expert voices from a clinical psychologist, Samaritans, and an employer.

## Act 4 — Solutions

Highlights Andy's Man Club, CALM, Samaritans, workplace mental health initiatives, and NHS Talking Therapies. Closes with:

"Talking is not weakness. Silence has a cost."

# Data Analytics Component

## Dashboard Sections (Power BI + Streamlit)

| Dashboard Tab | Content |
| --- | --- |
| Overview | Total male suicides by year, male vs female rate, KPI cards |
| Age Analysis | Rates by 5-year age band (18–24 through 55–65), 20-year trends |
| Regional Map | Choropleth: England by region + Scotland, Wales, Northern Ireland |
| Trend Analysis | 2000–2024 time series with annotated events (2008 crisis, COVID, 2022 spike) |
| Risk Factors | Deprivation scatter plot, employment correlation, rural vs urban |
| Predictive Heatmap | ML model output — risk score by local authority |

## Predictive Analytics Component

Using UK data from 2000–2024, the project builds a model to predict male suicide risk at local authority level. Features include deprivation score, unemployment rate, GP referral rate, alcohol admissions, and rural index. Models tested: Linear Regression (baseline) → Random Forest (feature importance) → Gradient Boosting (prediction). Output: risk heatmap deployed in Streamlit, accessible publicly without a Power BI licence.

## Technology Stack

| Tool | Purpose |
| --- | --- |
| Power BI | Primary dashboard — professional/employer use |
| Streamlit (Python) | Public web app — free, deployable via Streamlit Cloud |
| Python (Pandas, Plotly, Scikit-learn) | Data cleaning, EDA, predictive model |
| Jupyter Notebook | Analysis documentation for GitHub |
| GitHub | Version control, portfolio, public repository |

# 8-Week Project Timeline

## Phase 1 — Define the Problem (Week 1)

Goal: Establish focused project scope. Deliverables: one-page project brief, research questions, success criteria, GitHub repository initialised, folder structure created.

### Key Research Questions

- Why do men die by suicide at significantly higher rates than women in the UK?

- Which age group faces the greatest risk — and has that changed over time?

- How do regional differences within the UK compare?

- What social and economic factors show the strongest correlation?

- Are there patterns that predict elevated risk at local authority level?

- What interventions have shown measurable effectiveness?

## Phase 2 — Research and Data Collection (Week 2)

Goal: Gather reliable, high-quality data from primary sources.

| Source | Data Available | URL |
| --- | --- | --- |
| ONS Suicides Reference Tables | Deaths by sex, age, region, method (2001–2024) | ons.gov.uk/...suicidesintheukref... |
| Public Health Scotland | Scotland suicide data | publichealthscotland.scot |
| NISRA | Northern Ireland data | nisra.gov.uk |
| Samaritans Annual Report | UK-wide narrative + trends | samaritans.org |
| IMD 2019 | English deprivation by area | gov.uk/...deprivation-2019 |

## Phase 3 — Data Cleaning and Analysis (Week 3)

Goal: Transform raw data into analysis-ready datasets. Tasks include loading ONS Excel files into Python, standardising age categories across UK nations, merging deprivation data, calculating year-over-year changes, and building a correlation matrix.

Deliverables: Cleaned merged dataset (CSV), Jupyter EDA notebook, correlation analysis, initial findings document.

## Phase 4 — Dashboard Development (Week 4)

Goal: Build Power BI dashboard and begin Streamlit app scaffolding. Power BI covers 6 tabs (Overview, Age, Region, Trend, Risk Factors, Predictive Heatmap). Streamlit app skeleton with navigation, CSV data connections, and choropleth map (Plotly).

## Phase 5 — Story Development (Week 5)

Goal: Develop documentary story structure and character profiles. Write detailed backstories for 5 characters, plan interview questions, build scene storyboard, identify potential real interview subjects.

## Phase 6 — Predictive Model + Script Writing (Week 6)

Goal A (Analytics): Build and validate predictive risk model — feature engineering, Linear Regression baseline, Random Forest, Gradient Boosting, validation on 2019–2024 data, output risk scores.

Goal B (Script): Complete the full 10–20 page documentary script covering all four acts, narration text, and scene notes.

## Phase 7 — Content Creation (Week 7)

Goal: Produce all portfolio-ready assets — infographics (3–5), LinkedIn carousel, presentation deck (15 slides), Streamlit app completed and deployed, GitHub repository populated, final report written.

### GitHub Repository Structure

silent-burden-uk-male-suicide/ → README.md, data/ (raw + cleaned), notebooks/ (cleaning, EDA, model), dashboard/ (.pbix), streamlit_app/ (app.py + pages/), script/ (documentary_script.md), report/ (findings_report.pdf)

## Phase 8 — Publication and Awareness Campaign (Week 8)

Goal: Launch the project publicly. Publish GitHub repository, LinkedIn article, 3 LinkedIn posts, Streamlit app (live URL), Power BI Service dashboard, documentary video (if produced).

### LinkedIn Campaign Plan

- Post 1 (Monday): Personal story + project announcement

- Post 2 (Wednesday): 3 key data findings with infographic

- Post 3 (Friday): Call to action — resources and collaboration invite

- Article: Full 800–1,200 word LinkedIn piece summarising the project

# Portfolio Outputs Checklist

## Analytics

- Cleaned, merged dataset (CSV / Excel)

- Exploratory data analysis notebook (Jupyter)

- Predictive model notebook (Python)

- Interactive Power BI dashboard (.pbix)

- Streamlit web app (deployed, public URL)

- Predicted risk heatmap

## Storytelling

- Full documentary script (10–20 pages)

- Character profiles (5 main characters)

- Interview question guide

- Scene storyboard

## Communication

- Written findings report (PDF, 1,500–2,000 words)

- Presentation deck (15 slides — NHS/public health audience)

- LinkedIn article

- LinkedIn posts x 3

- Infographics x 3–5

## Technical

- GitHub repository (public)

- Streamlit app URL (shareable)

- README.md with project description, data sources, methodology

# Why This Project Stands Out

A good rule: 40% data, 40% storytelling, 20% awareness. The strongest projects do not stop at showing statistics — they explain what those statistics mean for real people.

Most entry-level data analytics portfolios show technical skills on business datasets. This project demonstrates: technical rigour using real ONS/NHS data; communication translating data into a human story; social impact working on a real public health crisis; predictive thinking moving beyond description; and professional presence through a public LinkedIn campaign.

If you are struggling, you do not have to carry this alone.

Samaritans: 116 123  |  CALM: 0800 58 58 58 (5pm–midnight)  |  andysmanclub.co.uk